## Summary
FolioBuddy User Story Tracker
Metric | Value | Area | Stories | Pass | Needs Test | Fail
Total stories | 71 | App Shell | 8 | 8 | 0 | 0
Pass | 71 | Auth and Runtime | 5 | 5 | 0 | 0
Needs Test | 0 | Backend API | 7 | 7 | 0 | 0
Fail | 0 | Dashboard | 7 | 7 | 0 | 0
Blocked | 0 | Dev Demo Mode | 2 | 2 | 0 | 0
Open defects | 0 | History | 5 | 5 | 0 | 0
|  | Investors | 4 | 4 | 0 | 0
Canonical file |  | Operations | 3 | 3 | 0 | 0
C:\Users\User\dev\ClaudeProjs\projects\foliobuddy\docs\qa\foliobuddy-user-story-tracker.xlsx |  | Portfolio | 17 | 17 | 0 | 0
Latest QA evidence |  | Settings | 4 | 4 | 0 | 0
C:/Users/User/dev/ClaudeProjs/projects/foliobuddy/.codex-qa/current-user-story-run/fresh-smoke-2026-06-24T08-11-45Z/evidence.json |  | Trades | 9 | 9 | 0 | 0
Operating rule
Update this workbook as the single source of truth whenever a story is added, a defect is found, a fix lands, or a retest changes status.

## Stories
Story ID | Feature Area | Route/Surface | Role | User Story | Expected Behavior | Edge Cases | Code Sources | Test Status | Test Method | Evidence | Defect IDs | Fix Status | Retest Status | Last Verified | Notes
AUTH-001 | Auth and Runtime | / | Signed-out visitor | As a signed-out visitor, I want to see only the sign-in surface so private portfolio data is protected. | The root route renders the FolioBuddy sign-in screen with Clerk SignIn, does not render private pages, and does not expose seeded dashboard data before authentication. | Missing Clerk publishable key, expired session, narrow mobile sign-in layout. | packages/frontend/src/App.tsx; docs/qa/user-facing-inventory.md | Pass | Playwright signed-out route plus static code review | docs/qa/2026-06-23-real-local-scale-qa.md signed-out auth pass |  | N/A | Pass | 2026-06-24 | Temporary port 4002 run verified signed-out Clerk surface.
AUTH-002 | Auth and Runtime | All protected routes | Signed-in user | As a signed-in user, I want all portfolio, trade, snapshot, investor, and export data scoped to my own account. | Frontend requests include a Clerk token when available; backend ensureUser creates missing users and mutation routes filter by req.userId or ownership guards. | Guessed IDs, stale token, optimistic rollback, shared global assets. | packages/frontend/src/lib/api.ts; packages/backend/src/middleware/auth.ts; packages/backend/src/routes/*; packages/backend/src/lib/authorization.ts | Pass | Backend route tests and code review | packages/backend/src/__tests__/routes/positions.test.ts; routes/trades.test.ts; routes/assets.test.ts |  | N/A | Pass | 2026-06-24 | Browser local bypass covers local user flows; user scoping is primarily route-test evidence.
AUTH-003 | Auth and Runtime | Local QA bypass | Local QA user | As a local QA user, I want to exercise real API routes without Clerk credentials in development only. | Backend bypass is ignored in production; frontend bypass requires Vite dev mode, skips ClerkProvider, installs a no-token API getter, shows LB avatar, and leaves websocket disconnected. | Frontend flag without backend flag, CORS missing Vite origin, production env accidentally set. | packages/frontend/src/lib/localAuthBypass.ts; packages/frontend/src/App.tsx; packages/frontend/src/hooks/useAuthSetup.ts; packages/backend/src/middleware/auth.ts | Pass | Local stack QA plus unit tests | docs/qa/2026-06-23-real-local-scale-qa.md BUG-003 and BUG-007 | BUG-003; BUG-007 | Fixed | Pass | 2026-06-24 | Used for final clean inventory at http://127.0.0.1:4000 with local backend.
AUTH-004 | Auth and Runtime | Global asset catalog | Admin asset maintainer | As an admin, I want global asset catalog edits restricted so shared assets cannot be changed by normal users. | PUT/DELETE global asset routes require ADMIN_USER_IDS; per-user refresh and NAV routes require current-user asset ownership. | Non-admin catalog mutation, unowned asset refresh, shared asset with many holders. | packages/backend/src/lib/authorization.ts; packages/backend/src/routes/assets.ts; packages/backend/src/__tests__/routes/assets.test.ts | Pass | Backend route tests | docs/qa/2026-06-23-real-local-scale-qa.md admin guard |  | N/A | Pass | 2026-06-24 | Admin write path not executed in browser; covered by API tests.
AUTH-005 | Auth and Runtime | WebSocket client/server | Authenticated user | As an authenticated user, I want live price and portfolio changes to update data without manually refreshing. | Socket.io connects with Clerk token, price broadcasts invalidate all clients, portfolio updates are scoped to the user's room, and unauthenticated sockets are rejected. | Disconnect/reconnect, bad origin, local bypass without Clerk, user-room leakage. | packages/backend/src/services/socketService.ts; packages/frontend/src/hooks/useWebSocket.ts; packages/backend/src/__tests__/socketService.integration.test.ts; packages/frontend/src/hooks/__tests__/useWebSocket.test.ts | Pass | Socket.io integration harness and frontend hook tests | docs/qa/user-facing-inventory.md latest rerun status |  | N/A | Pass | 2026-06-24 | Local bypass intentionally shows disconnected status.
SHELL-001 | App Shell | Sidebar navigation | Signed-in user | As a user, I want sidebar links and keyboard hints so I can move between major pages quickly. | Dashboard, Portfolio, Trades, History, Investors, and Settings links route within the SPA, active route is highlighted, and shortcuts are listed. | Collapsed desktop rail, active route after route change, basePath in demo mode. | packages/frontend/src/components/layout/AppShell.tsx; packages/frontend/src/hooks/useKeyboardShortcuts.ts | Pass | Clean local route matrix and safe open-state pass | C:/Users/User/dev/ClaudeProjs/projects/foliobuddy/.codex-qa/current-user-story-run/fresh-smoke-2026-06-24T08-11-45Z/evidence.json |  | N/A | Pass | 2026-06-24 | Route matrix passed 7/7 including mobile route.
SHELL-002 | App Shell | Mobile drawer | Mobile user | As a mobile user, I want a drawer menu so all routes remain reachable on small screens. | Hamburger opens the drawer, overlay closes it, drawer links navigate and then close. | 390px viewport, scrollable route content, drawer overlay tap target. | packages/frontend/src/components/layout/AppShell.tsx | Pass | Playwright mobile smoke | .codex-qa/clean-inventory-2026-06-24T12-46-01/mobile-trades.png |  | N/A | Pass | 2026-06-24 | Mobile drawer navigation Portfolio to Trades passed.
SHELL-003 | App Shell | Desktop sidebar collapse | Desktop user | As a desktop user, I want to collapse the sidebar so dense data pages get more horizontal room. | Collapse/expand button toggles width, persists in localStorage, and shows tooltips for icon-only nav. | localStorage unavailable, reload persistence, tooltip on collapsed nav. | packages/frontend/src/components/layout/AppShell.tsx | Pass | Static code review plus prior QA route pass | docs/qa/2026-06-23-production-scale-demo-qa.md app shell |  | N/A | Pass | 2026-06-24 | No current automated assertion for persistence; tracked as covered by code and manual QA.
SHELL-004 | App Shell | Keyboard shortcuts | Power user | As a power user, I want keyboard shortcuts for navigation, theme, and help. | D/P/T/H/I/S navigate; slash cycles theme; Cmd/Ctrl+K opens help; shortcuts do not fire while typing in form fields. | Input focus, textarea focus, browser shortcut conflicts. | packages/frontend/src/hooks/useKeyboardShortcuts.ts; packages/frontend/src/components/layout/ShortcutsHelpModal.tsx | Pass | Safe open-state pass plus code review | docs/qa/2026-06-23-real-local-scale-qa.md safe open-state pass |  | N/A | Pass | 2026-06-24 | Help modal opened via Ctrl+K during safe pass.
SHELL-005 | App Shell | Currency toggle | Signed-in user | As a user, I want to switch display currency between USD and SGD. | The shell currency button toggles the Zustand currency store; pages convert displayed values without changing stored USD data. | Missing FX row, reload persistence, new tab. | packages/frontend/src/components/layout/AppShell.tsx; packages/frontend/src/stores/currencyStore.ts; packages/frontend/src/lib/utils.ts | Pass | Settings/local QA plus store code review | docs/qa/2026-06-23-real-local-scale-qa.md settings and shell pass |  | N/A | Pass | 2026-06-24 | Settings select also covers the same store.
SHELL-006 | App Shell | Theme toggle | Signed-in user | As a user, I want to cycle light/dark/system appearance. | Shell icon cycles light and dark; Settings select can set light, dark, or system; theme applies through document class without layout breakage. | System theme change, invalid stored value, shortcut slash while typing. | packages/frontend/src/components/layout/AppShell.tsx; packages/frontend/src/stores/themeStore.ts; packages/frontend/src/hooks/useThemeEffect.ts | Pass | Safe open-state pass plus store code review | docs/qa/2026-06-23-real-local-scale-qa.md settings route |  | N/A | Pass | 2026-06-24 | Theme behavior was not mutation-bearing.
SHELL-007 | App Shell | Refresh prices action | Signed-in user | As a user, I want to refresh prices from the shell. | Clicking refresh calls api.refreshPrices, shows a spinner/status text, and invalidates cached queries on success. | Provider failure, rate limit, repeated clicks, mobile overflow menu. | packages/frontend/src/components/layout/AppShell.tsx; packages/backend/src/routes/prices.ts; packages/backend/src/services/priceService.ts | Pass | Safe open-state and backend tests | docs/qa/2026-06-23-real-local-scale-qa.md settings and shell |  | N/A | Pass | 2026-06-24 | Final safe pass did not perform write methods; API behavior covered by route/service tests.
SHELL-008 | App Shell | Export data action | Signed-in user | As a user, I want a one-click Excel export from the shell. | Clicking export opens the Excel export URL in a new tab; backend returns XLSX attachment with supported sheet names. | Popup blocked, ExcelJS protected sheet names, large datasets. | packages/frontend/src/components/layout/AppShell.tsx; packages/backend/src/routes/export.ts; packages/backend/src/__tests__/routes/export.test.ts | Pass | HEAD export check and regression test | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json exports | BUG-005 | Fixed | Pass | 2026-06-24 | Bodies were not downloaded during safe pass.
DASH-001 | Dashboard | / | Investor owner | As the primary owner, I want the dashboard to default to my stake so the headline net worth matches my view. | Investor filter defaults to the owner row when present; All/Clear can select or clear investor checkboxes; label reflects selected investors. | No owner, multiple owners, zero-stake observer, all investors cleared. | packages/frontend/src/pages/Dashboard.tsx; packages/frontend/src/components/dashboard/NetWorthCard.tsx | Pass | Clean route matrix and investor popover pass | .codex-qa/clean-inventory-2026-06-24T12-46-01/dashboard.png |  | N/A | Pass | 2026-06-24 | Final evidence expected Net Worth (Scale Owner).
DASH-002 | Dashboard | DB health banner | Signed-in user | As a user, I want database health surfaced when the dashboard loads. | Dashboard shows the DB status banner from /health/db without blocking other dashboard content. | Backend down, slow DB latency, health route error. | packages/frontend/src/components/dashboard/DbStatusBanner.tsx; packages/backend/src/routes/health.ts | Pass | Clean route matrix and API health check | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json api.health |  | N/A | Pass | 2026-06-24 | API health latency was 2 ms in final evidence.
DASH-003 | Dashboard | Net worth hero | Signed-in user | As a user, I want a concise net worth hero with YTD, 30D, exposure, positions, and trades. | The hero uses portfolio summary, selected investor stake multiplier, 30D performance start, owned market exposure plus perp exposure, and closed trade analytics. | Empty portfolio, no performance history, negative PnL, custody rows. | packages/frontend/src/pages/Dashboard.tsx; packages/frontend/src/components/dashboard/NetWorthCard.tsx; packages/backend/src/services/portfolioService.ts | Pass | Clean route matrix | .codex-qa/clean-inventory-2026-06-24T12-46-01/dashboard.png |  | N/A | Pass | 2026-06-24 | Custody exclusion covered in portfolio summary tests and QA inventory.
DASH-004 | Dashboard | Portfolio value chart | Signed-in user | As a user, I want portfolio value over selectable periods including Max. | Period buttons request the right date window; Max sends all=true; chart shows value history, reference line, end label, and loading state on period changes. | No snapshots, 390 points, YTD boundary, Max older than 1Y. | packages/frontend/src/components/dashboard/PortfolioChart.tsx; packages/frontend/src/lib/chartUtils.ts; packages/backend/src/routes/snapshots.ts | Pass | Clean route matrix plus unit tests | packages/frontend/src/lib/__tests__/chartUtils.test.ts; .codex-qa evidence dashboard route |  | N/A | Pass | 2026-06-24 | Final route matrix expected Portfolio $ Value.
DASH-005 | Dashboard | Benchmark comparison chart | Signed-in user | As a user, I want portfolio percent performance compared to BTC, ETH, SPX, and custom benchmarks. | Default benchmarks render; custom benchmarks can be searched, added up to the limit, toggled, removed; provider history fallback uses stored PriceHistory when live provider history fails. | Provider outage, duplicate benchmark, no search results, SPX Yahoo fallback. | packages/frontend/src/components/dashboard/BenchmarkComparisonChart.tsx; packages/frontend/src/lib/benchmarkUtils.ts; packages/backend/src/services/priceService.ts | Pass | Clean route matrix, benchmark control pass, backend service tests | docs/qa/2026-06-23-real-local-scale-qa.md BUG-009 and benchmark controls | BUG-009 | Fixed | Pass | 2026-06-24 | Final evidence recorded zero bad provider-history API responses.
DASH-006 | Dashboard | Allocation donuts | Signed-in user | As a user, I want allocation charts by asset, detailed asset, storage, and cash breakdown. | Four donuts render from owned positions only, group crypto sub-2 percent slices into Other when needed, use chart colors, and provide category detail selection. | Custody rows, empty cash, duplicate assets, many storage locations, legend overflow. | packages/frontend/src/components/dashboard/AllocationCharts.tsx; packages/frontend/src/lib/chartColors.ts | Pass | Clean route matrix screenshot | .codex-qa/clean-inventory-2026-06-24T12-46-01/dashboard.png |  | N/A | Pass | 2026-06-24 | Final seeded dataset included crypto, equities, cash, storage, and custody.
DASH-007 | Dashboard | Performers lists | Signed-in user | As a user, I want top and worst performers ranked by absolute unrealized PnL. | Top and worst lists render duplicate asset IDs safely and rank by USD PnL impact rather than percentage. | Repeated cash asset IDs, negative PnL, empty performer list. | packages/frontend/src/components/dashboard/PerformersCard.tsx; packages/backend/src/services/portfolioService.ts | Pass | Unit test and clean route matrix | packages/frontend/src/components/dashboard/__tests__/PerformersCard.test.tsx; docs/qa/2026-06-23-production-scale-demo-qa.md BUG-002 | BUG-002 | Fixed | Pass | 2026-06-24 | Duplicate key regression covered.
PORT-001 | Portfolio | /portfolio | Signed-in user | As a user, I want a portfolio hero that summarizes total value, YTD start, exposure, positions, and YTD PnL. | Portfolio header uses summary data, currency conversion, owned market exposure plus local perp exposure, and responsive stat layout. | No positions, negative PnL, mobile 2-column summary, missing FX. | packages/frontend/src/pages/Portfolio.tsx; packages/backend/src/services/portfolioService.ts | Pass | Clean route matrix | .codex-qa/clean-inventory-2026-06-24T12-46-01/portfolio.png |  | N/A | Pass | 2026-06-24 | Final evidence showed 63 positions.
PORT-002 | Portfolio | Category sections | Signed-in user | As a user, I want positions grouped into Crypto, Equities, Cash, and Held for Others. | Owned positions are grouped by category; custody positions are separated, purple, collapsed by default, and excluded from totals/allocations/exposure. | Same asset owned and custody, empty categories, custom custody names. | packages/frontend/src/pages/Portfolio.tsx; packages/frontend/src/components/portfolio/CollapsibleCard.tsx; packages/shared/src/types.ts | Pass | Clean route matrix | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json routes /portfolio |  | N/A | Pass | 2026-06-24 | Expected counts: Crypto 24, Equities 26, Cash 10, Held for Others 3.
PORT-003 | Portfolio | Position table | Signed-in user | As a user, I want each section table to show values, price, average cost, PnL, storage, and row actions. | Rows format per-unit prices with smart decimals, quantities by asset type, local native price second lines where applicable, and row actions for view/copy/NAV/edit/delete. | Local-currency equity, unit trust manual NAV age, mobile compact columns, duplicate assets. | packages/frontend/src/components/portfolio/PositionTable.tsx; PositionRow.tsx; positionPriceDisplay.ts; packages/frontend/src/lib/utils.ts | Pass | Clean route matrix and mobile smoke | .codex-qa/clean-inventory-2026-06-24T12-46-01/portfolio.png |  | N/A | Pass | 2026-06-24 | Mobile compact/all columns toggles were usable.
PORT-004 | Portfolio | Equity grouping toggle | Signed-in user | As a user, I want equities grouped by broker or by type. | The By Broker/By Type segmented control changes PositionTable grouping and persists to localStorage. | Invalid stored value, no equities, only unit trusts. | packages/frontend/src/pages/Portfolio.tsx; packages/frontend/src/components/portfolio/PositionTable.tsx | Pass | Static code review and route QA | docs/qa/user-facing-inventory.md Portfolio |  | N/A | Pass | 2026-06-24 | Grouping state key: foliobuddy-equity-group-by.
PORT-005 | Portfolio | Perp exposure dialog | Signed-in user | As a user, I want to record local perpetual futures exposure so exposure metrics are accurate without affecting net worth. | Cash section exposes Add/Edit Perp, stores value in localStorage with legacy migration, and includes it in exposure calculations only. | Legacy key, invalid number, mobile dialog, zero exposure. | packages/frontend/src/pages/Portfolio.tsx | Pass | Static code review and prior QA | docs/qa/user-facing-inventory.md Client State Inventory |  | N/A | Pass | 2026-06-24 | No write API involved.
PORT-006 | Portfolio | Add position form | Signed-in user | As a user, I want to add crypto, cash, equity, unit-trust, NFT, and angel positions manually. | Add Position opens a form with category-specific fields, asset search/create flows, quantity/cost inputs, storage, notes, custody, and submit gating that matches backend validation. | Crypto, stablecoin, fiat cash, stock/ETF, unit trust, NFT, angel, custom storage, custody. | packages/frontend/src/components/portfolio/PositionForm.tsx; AssetSearchDropdown.tsx; PositionCostFields.tsx; PositionStorageFields.tsx; packages/backend/src/routes/positions.ts | Pass | Safe open-state pass, invalid guard pass, backend route tests | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json interactions Add Position invalid guard | BUG-008 | Fixed | Pass | 2026-06-24 | Negative quantity clears and submit remains disabled.
PORT-007 | Portfolio | Asset search/create | Signed-in user | As a user, I want searchable provider assets and manual assets so new positions can be attached to correct instruments. | Crypto uses CoinGecko; equities and benchmarks use Yahoo; unit trusts can be manual/yahoo with native currency, ISIN, factsheet, and NAV fields. | Yahoo regional search fallback, local exchange suffixes, duplicate symbols, no results. | packages/frontend/src/components/portfolio/AssetSearchDropdown.tsx; packages/backend/src/routes/assets.ts; packages/backend/src/services/providers/YahooFinanceProvider.ts | Pass | Backend provider tests and form code review | packages/backend/src/__tests__/YahooFinanceProvider.test.ts |  | N/A | Pass | 2026-06-24 | Kioxia, Taiwan, Korea, Oslo coverage lives in provider tests.
PORT-008 | Portfolio | Fiat cash and stablecoins | Signed-in user | As a user, I want cash to support both stablecoins and fiat balances. | Cash form lets users select stablecoin or Cash (fiat); fiat reveals currency, uses manual CASH assets, and restricts storage to broker/bank. | SGD fallback versus real FX, changing type after storage selected, bank defaults. | packages/frontend/src/components/portfolio/PositionForm.tsx; positionOptions.ts; packages/backend/src/routes/assets.ts | Pass | Static code review plus route QA | docs/qa/user-facing-inventory.md Cash Positions |  | N/A | Pass | 2026-06-24 | Seed data includes USD/SGD cash and stablecoins.
PORT-009 | Portfolio | Local-currency equities | Signed-in user | As a user, I want listed equities in SGD/JPY/TWD/KRW/NOK to use local cost inputs and USD persistence. | Create/edit waits for a real FX row before non-USD cost conversion; display shows app currency primary and muted native price/avg-cost second line. | FX rates still loading, zero-decimal currencies, edit initialized from stored USD. | packages/frontend/src/components/portfolio/PositionForm.tsx; positionPriceDisplay.ts; packages/backend/src/routes/fx.ts; packages/backend/src/lib/fxConstants.ts | Pass | Static code review and provider tests | docs/qa/user-facing-inventory.md Equity Positions |  | N/A | Pass | 2026-06-24 | Seed data includes local-currency equity.
PORT-010 | Portfolio | Unit trust manual NAV | Signed-in user | As a unit-trust holder, I want manual NAV updates and age badges so stale pricing is visible. | Manual-priced non-cash positions and unit trusts show NAV age; Update NAV modal patches asset NAV, updates price date/notes, and recomputes visible linked position values. | Invalid NAV, old NAV date, multiple positions share one manual asset. | packages/frontend/src/components/portfolio/UpdateNavModal.tsx; PositionTable.tsx; packages/backend/src/routes/assets.ts | Pass | Safe open-state pass plus demo/API tests | docs/qa/2026-06-23-production-scale-demo-qa.md BUG-001; docs/qa/2026-06-23-real-local-scale-qa.md | BUG-001 | Fixed | Pass | 2026-06-24 | NAV dialog opened in safe pass; demo mutation coverage exists.
PORT-011 | Portfolio | Unit trust PDF import | Signed-in user | As a unit-trust holder, I want broker PDF statements parsed into holdings to avoid manual typing. | PDF upload accepts PDF only, parses UOB Kay Hian and FSMOne statements, returns holdings, and matches imported holdings to existing unit-trust positions by ISIN/provider/symbol/name/location. | Flattened PDF table text, broker tie-break, malformed PDF, unsupported broker. | packages/backend/src/routes/assets.ts; packages/backend/src/services/statementParsers/uobKayHian.ts; fsmOne.ts; packages/frontend/src/components/portfolio/statementMatching.ts | Pass | Parser and matching unit tests | packages/backend/src/__tests__/uobKayHianParser.test.ts if present; fsmOneParser.test.ts; packages/frontend/src/components/portfolio/__tests__/statementMatching.test.ts |  | N/A | Pass | 2026-06-24 | Statement matching coverage is explicit; browser file-upload path remains non-destructive in safe QA.
PORT-012 | Portfolio | Edit totals | Signed-in user | As a user, I want to correct a position's total quantity/cost when historical data needs a reset. | Edit Totals tab updates quantity/cost/asset/storage/custody, creates a reset history boundary when aggregate values change, and preserves validation. | Clearing custody, asset change, stale totals, reset row display. | packages/frontend/src/components/portfolio/PositionForm.tsx; packages/backend/src/routes/positions.ts | Pass | Backend route tests and form code review | packages/backend/src/__tests__/routes/positions.test.ts |  | N/A | Pass | 2026-06-24 | Manual reset history described in AGENTS/FORET and covered by route tests.
PORT-013 | Portfolio | Add/reduce position | Signed-in user | As a user, I want to add or reduce a position while preserving weighted average cost correctly. | Add asks for quantity and cost, reduce asks for quantity only, preview shows old/new totals, backend validates delta metadata, and add/reduce history is written transactionally. | Reduce to zero, funded add, stale current totals, skip-confirm localStorage. | packages/frontend/src/components/portfolio/PositionDeltaEditor.tsx; positionFormMath.ts; packages/backend/src/routes/positions.ts; packages/shared/src/types.ts | Pass | Unit tests and backend route tests | packages/frontend/src/components/portfolio/__tests__/positionFormMath.test.ts; packages/backend/src/__tests__/routes/positions.test.ts |  | N/A | Pass | 2026-06-24 | Pure helper shared by preview and submit path.
PORT-014 | Portfolio | Cancel position history | Signed-in user | As a user, I want to cancel the newest safe add/reduce entry if I made a mistake. | Only the newest add/reduce history row can be canceled when current totals still match; funded add cancellation restores linked cash pile via operationId. | Older row, reset row, current totals changed, linked cash restore. | packages/backend/src/routes/positions.ts; packages/frontend/src/components/portfolio/PositionRow.tsx | Pass | Backend route tests | packages/backend/src/__tests__/routes/positions.test.ts |  | N/A | Pass | 2026-06-24 | Not executed destructively in browser safe pass.
PORT-015 | Portfolio | Copy and export positions | Signed-in user | As a user, I want to copy positions or export them to CSV/Excel. | Copy All writes JSON for all positions; row copy writes one position; CSV and Excel export URLs return attachments. | Clipboard permission denied, empty portfolio, popup blocked, large export. | packages/frontend/src/components/portfolio/positionClipboard.ts; packages/backend/src/routes/export.ts | Pass | Clipboard pass and HEAD export checks | docs/qa/2026-06-23-real-local-scale-qa.md Copy, Export, Validation, And Auth Pass | BUG-005 | Fixed | Pass | 2026-06-24 | Final export HEAD checks passed 5/5.
PORT-016 | Portfolio | Delete positions | Signed-in user | As a user, I want row delete and delete-all flows protected by confirmations. | Delete dialogs show target/count, Cancel closes with no mutation, confirmed delete invalidates queries and rolls back optimistic state on error. | Cancel path, failed delete rollback, skip confirmation setting, delete all. | packages/frontend/src/pages/Portfolio.tsx; packages/frontend/src/hooks/usePortfolio.ts; packages/backend/src/routes/positions.ts | Pass | Destructive cancel rerun and backend tests | docs/qa/2026-06-23-real-local-scale-qa.md destructive cancel rerun |  | N/A | Pass | 2026-06-24 | Confirming destructive delete was not performed in safe browser pass.
PORT-017 | Portfolio | JSON bulk import | Signed-in user | As a user, I want to paste/import positions in bulk from JSON. | Import tab parses JSON, honors existing asset matching, returns per-row success/error results, and updates visible positions on success. | Malformed JSON, existing symbol, provider metadata, custody fields. | packages/frontend/src/components/portfolio/PositionImportTab.tsx; packages/backend/src/routes/positions.ts; packages/frontend/src/dev/demoMode.tsx | Pass | Demo import QA and backend route tests | docs/qa/2026-06-23-production-scale-demo-qa.md BUG-001 | BUG-001 | Fixed | Pass | 2026-06-24 | Demo mock now mutates visible state for import workflows.
TRADE-001 | Trades | /trades | Trader | As a trader, I want a trade tape with All/Open/Closed filters. | The table fetches all trades once, filters locally by status, and counts match visible rows across all lenses. | Open trade without exit, 240 rows, ticker-filtered counts. | packages/frontend/src/pages/Trades.tsx; packages/frontend/src/components/trades/TradeTapeSection.tsx; packages/backend/src/routes/trades.ts | Pass | Clean route matrix | .codex-qa/clean-inventory-2026-06-24T12-46-01/trades.png |  | N/A | Pass | 2026-06-24 | Expected All 240, Open 40, Closed 200.
TRADE-002 | Trades | Review lens | Trader | As a trader, I want review stats and ticker PnL before the tape. | Review lens shows collapsed trade stats, collapsed ticker PnL, and shared tape; notable trade clicks highlight the row. | No trades, duplicate ticker, large win/loss. | packages/frontend/src/pages/Trades.tsx; packages/frontend/src/components/dashboard/TradeStatsCard.tsx; packages/frontend/src/components/trades/TickerPnLCard.tsx | Pass | Clean route matrix and component tests | packages/frontend/src/components/trades/__tests__/TickerPnLCard.test.tsx |  | N/A | Pass | 2026-06-24 | Subtitle currently reports analytics closed-trade total from API.
TRADE-003 | Trades | Ticker dossier lens | Trader | As a trader, I want to focus on one ticker's performance and recent trades. | Ticker lens derives dossiers from fetched trades, supports ticker chip navigation, shows PnL/win-rate/hold stats/tags, and clears ticker query param. | No selected ticker, ticker with only open trades, repeated symbol. | packages/frontend/src/components/trades/TradeLensViews.tsx; tradeLensModels.ts; packages/frontend/src/pages/Trades.tsx | Pass | Safe open-state pass and pure model tests by code review | docs/qa/2026-06-23-real-local-scale-qa.md Safe Open-State Pass |  | N/A | Pass | 2026-06-24 | Ticker lens switched during safe pass.
TRADE-004 | Trades | Monthly postmortem lens | Trader | As a trader, I want monthly postmortems to review repeatable edges and loss patterns. | Monthly lens builds month summaries, repeatable-edge tags, loss review, and open-trade watchlist from the same trade dataset. | Month with only open trades, no tags, large losses. | packages/frontend/src/components/trades/TradeLensViews.tsx; tradeLensModels.ts | Pass | Safe open-state pass | docs/qa/2026-06-23-real-local-scale-qa.md Interaction Evidence |  | N/A | Pass | 2026-06-24 | Monthly lens rendered against 240 trades.
TRADE-005 | Trades | Trade row detail | Trader | As a trader, I want to open trade details by mouse or keyboard. | Rows are clickable and keyboard activatable with Enter/Space; action cells stop propagation; detail dialog supports copy/edit/delete. | Keyboard focus, action icon click, highlighted row after stat click. | packages/frontend/src/components/trades/TradeTable.tsx; TradeDetailDialog.tsx | Pass | Playwright interaction pass | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json interactions Trade row detail open |  | N/A | Pass | 2026-06-24 | Final interaction evidence passed.
TRADE-006 | Trades | Log trade form | Trader | As a trader, I want to log long/short open or closed trades. | Form requires asset, positive quantity, positive entry price, optional exit price/date for closed trades, and computes direction/status/PnL through backend. | Short PnL, zero quantity, negative price, exit before entry, missing exit price. | packages/frontend/src/components/trades/TradeForm.tsx; packages/backend/src/routes/trades.ts; packages/backend/src/lib/tradePnL.ts | Pass | Invalid guard pass and backend route/unit tests | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json interactions Log Trade invalid quantity guard | BUG-008 | Fixed | Pass | 2026-06-24 | Zero quantity leaves submit disabled.
TRADE-007 | Trades | Edit and close trade | Trader | As a trader, I want to edit a trade or close an open trade. | Edit dialog reuses TradeForm; close endpoint updates exit price/date/notes and realized PnL; mutations invalidate trade analytics and list data. | Open trade close without exit date, stale analytics, failed mutation rollback. | packages/frontend/src/pages/Trades.tsx; packages/frontend/src/components/trades/TradeForm.tsx; packages/backend/src/routes/trades.ts | Pass | Backend route tests and open-state QA | packages/backend/src/__tests__/routes/trades.test.ts |  | N/A | Pass | 2026-06-24 | Safe pass opened edit path; close mutation covered by API tests.
TRADE-008 | Trades | Trade import | Trader | As a trader, I want to import trades from JSON with per-row results. | Import tab parses JSON array, normalizes assets, calls bulk-import, and displays success/error results. | Malformed JSON, duplicate asset symbol, open trades, short trades. | packages/frontend/src/components/trades/TradeImportTab.tsx; packages/backend/src/routes/trades.ts; packages/frontend/src/dev/demoMode.tsx | Pass | Demo import QA and backend route tests | docs/qa/2026-06-23-production-scale-demo-qa.md BUG-001 | BUG-001 | Fixed | Pass | 2026-06-24 | Demo mock now returns results array and mutates analytics.
TRADE-009 | Trades | Copy/export/delete trades | Trader | As a trader, I want to copy, export, or delete trade records. | Copy All/row/detail write JSON; export all/open/closed trade CSVs return attachments; delete dialogs cancel safely and confirmed deletes invalidate queries. | Clipboard permission, empty list, export filter, cancel path, failed delete rollback. | packages/frontend/src/components/trades/tradeClipboard.ts; packages/frontend/src/pages/Trades.tsx; packages/backend/src/routes/export.ts | Pass | Clipboard pass, HEAD export checks, destructive cancel rerun | docs/qa/2026-06-23-real-local-scale-qa.md Copy, Export, Validation, And Auth Pass |  | N/A | Pass | 2026-06-24 | Final export checks covered all/open/closed CSV.
HIST-001 | History | /history | Signed-in user | As a user, I want snapshot counts and source filters for portfolio history. | History fetches up to 500 snapshots, displays total/automatic/manual counts, and filters rows using Radix tabs. | 390 rows, API default pagination, source mismatch. | packages/frontend/src/pages/History.tsx; packages/frontend/src/hooks/useSnapshots.ts; packages/backend/src/routes/snapshots.ts | Pass | Clean route matrix and hook test | .codex-qa/clean-inventory-2026-06-24T12-46-01/history.png | BUG-004 | Fixed | Pass | 2026-06-24 | Final evidence expected All 390, Automatic 377, Manual 13.
HIST-002 | History | Snapshot table | Signed-in user | As a user, I want a table of snapshot values and returns with expandable positions. | Rows display formatted dates/values/returns, support copy/edit/delete actions, and expand automatic/manual rows to fetch nested snapshot positions. | Pending today snapshot, empty nested positions, large nested position set. | packages/frontend/src/components/history/SnapshotTable.tsx; packages/backend/src/routes/snapshots.ts | Pass | Copy/expand pass and backend route tests | docs/qa/2026-06-23-real-local-scale-qa.md Copy, Export, Validation, And Auth Pass |  | N/A | Pass | 2026-06-24 | Automatic row expanded 12 nested positions.
HIST-003 | History | Add/edit manual snapshot | Signed-in user | As a user, I want to add or correct a historical portfolio snapshot. | Form requires positive total value, supports date/type/source/notes, converts SGD display by FX rate, and disables submit for invalid numeric input. | Negative value, zero value, duplicate timestamp upsert, automatic row edit. | packages/frontend/src/components/history/SnapshotForm.tsx; packages/backend/src/routes/snapshots.ts; packages/frontend/src/components/ui/formatted-number-input.tsx | Pass | Invalid guard pass and backend route tests | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json interactions Add Snapshot negative value guard | BUG-006 | Fixed | Pass | 2026-06-24 | Entering -1 clears the field and creates no row.
HIST-004 | History | Snapshot import | Signed-in user | As a user, I want to import snapshots from JSON with per-row results. | Import tab parses JSON, posts bulk snapshots, updates counts/performance data, and surfaces success/error results. | Malformed JSON, duplicate timestamp, huge history. | packages/frontend/src/components/history/SnapshotImportTab.tsx; packages/backend/src/routes/snapshots.ts; packages/frontend/src/dev/demoMode.tsx | Pass | Demo import QA and backend route tests | docs/qa/2026-06-23-production-scale-demo-qa.md BUG-001 | BUG-001 | Fixed | Pass | 2026-06-24 | Demo mock now supports /snapshots/bulk.
HIST-005 | History | Copy/delete snapshots | Signed-in user | As a user, I want to copy snapshots and protect destructive deletes. | Copy All excludes pending today snapshots; row copy and copy positions write JSON; delete dialogs cancel safely and confirmed deletes mutate through owned routes. | Pending live row, cancel path, failed delete rollback, delete all. | packages/frontend/src/pages/History.tsx; packages/frontend/src/components/history/SnapshotTable.tsx; packages/backend/src/routes/snapshots.ts | Pass | Clipboard pass and destructive cancel rerun | docs/qa/2026-06-23-real-local-scale-qa.md Copy, Export, Validation, And Auth Pass | BUG-006 | Fixed | Pass | 2026-06-24 | Erroneous BUG-006 local row was approved and cleaned from local DB.
INV-001 | Investors | /investors | Investor owner | As a portfolio owner, I want a list of investors with stake and return values. | Investors page shows total investor count, allocated stake, available stake, total current value, owner badge, stake, capital at year start, current value, and YTD return. | No investors, 0% observer, total stake over/under 100, negative YTD. | packages/frontend/src/pages/Investors.tsx; packages/backend/src/routes/investors.ts | Pass | Clean route matrix | .codex-qa/clean-inventory-2026-06-24T12-46-01/investors.png |  | N/A | Pass | 2026-06-24 | Final evidence expected Scale Owner and Observer.
INV-002 | Investors | Add investor | Portfolio owner | As an owner, I want to add an investor with remaining stake calculated automatically. | Add form requires name, shows read-only suggested remaining stake, accepts optional capital, and can mark primary owner. | 100% allocated, blank name, optional capital blank, 0% remaining. | packages/frontend/src/pages/Investors.tsx; packages/backend/src/routes/investors.ts | Pass | Safe open-state and invalid guard pass | docs/qa/2026-06-23-real-local-scale-qa.md Interaction Evidence |  | N/A | Pass | 2026-06-24 | Empty submit starts disabled.
INV-003 | Investors | Edit investor | Portfolio owner | As an owner, I want to edit investor stake/capital/owner state. | Edit form allows stake percentage with up to 5 decimals, shows suggested balancing stake for owner, warns if projected total exceeds 100, and saves changes. | Stake 0, stake 100, projected total above 100, multiple owner flags. | packages/frontend/src/pages/Investors.tsx; packages/backend/src/routes/investors.ts | Pass | Safe open-state pass and backend route tests | packages/backend/src/__tests__/routes/investors.test.ts if present; docs/qa Interaction Evidence |  | N/A | Pass | 2026-06-24 | Backend investor routes are included in API client and QA inventory.
INV-004 | Investors | Delete investor | Portfolio owner | As an owner, I want deleting investors to handle stake reassignment safely. | Delete dialog shows investor name; when other investors exist, stake is reassigned automatically for two investors or via select for three-plus; cancel leaves counts unchanged. | Deleting last investor, deleting with assigned positions, no reassignment selected. | packages/frontend/src/pages/Investors.tsx; packages/backend/src/routes/investors.ts | Pass | Destructive cancel rerun and backend route tests | docs/qa/2026-06-23-real-local-scale-qa.md destructive cancel rerun |  | N/A | Pass | 2026-06-24 | Confirmed destructive delete not executed during safe pass.
SET-001 | Settings | /settings | Signed-in user | As a user, I want to choose default display currency. | Currency select updates the currency store, persists selection, and rerenders money across pages without altering backend data. | Missing FX, reload persistence, invalid stored value. | packages/frontend/src/pages/Settings.tsx; packages/frontend/src/stores/currencyStore.ts | Pass | Clean route matrix and code review | .codex-qa/clean-inventory-2026-06-24T12-46-01/settings.png |  | N/A | Pass | 2026-06-24 | Settings route rendered current FX block when available.
SET-002 | Settings | /settings | Signed-in user | As a user, I want to choose light/dark/system appearance. | Appearance select writes the theme store and useThemeEffect applies it. | System media change, invalid stored value. | packages/frontend/src/pages/Settings.tsx; packages/frontend/src/stores/themeStore.ts; packages/frontend/src/hooks/useThemeEffect.ts | Pass | Clean route matrix and code review | .codex-qa/clean-inventory-2026-06-24T12-46-01/settings.png |  | N/A | Pass | 2026-06-24
SET-003 | Settings | Data management | Signed-in user | As a user, I want to refresh prices, refresh FX rates, and create a snapshot from Settings. | Buttons show pending state, call the right API endpoints, invalidate related queries, and log non-fatal errors on failure. | Provider failure, missing FX row, snapshot duplicate, repeated clicks. | packages/frontend/src/pages/Settings.tsx; packages/backend/src/routes/prices.ts; routes/fx.ts; routes/snapshots.ts | Pass | Route rendering plus backend tests | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json routes /settings |  | N/A | Pass | 2026-06-24 | Final safe browser pass skipped write methods; API behavior covered separately.
SET-004 | Settings | Export data | Signed-in user | As a user, I want to export Excel, positions CSV, and trades CSV from Settings. | Export buttons open correct URLs and backend returns attachment headers for XLSX/CSV. | Popup blocked, Excel worksheet names, empty exports. | packages/frontend/src/pages/Settings.tsx; packages/backend/src/routes/export.ts | Pass | HEAD export checks and export test | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json exports | BUG-005 | Fixed | Pass | 2026-06-24 | Settings screenshot includes export controls.
DEMO-001 | Dev Demo Mode | /dev/demo/* | Developer/QA | As a developer, I want a dev-only demo route with production-shaped mocked API data. | Demo mode only exists in Vite dev, lazy-loads mock code, installs fetch/token mock before child routes render, and restores globals on unmount. | Production build, child route before mock ready, full refresh reset. | packages/frontend/src/App.tsx; packages/frontend/src/dev/demoMode.tsx; packages/frontend/src/dev/__tests__/demoMode.test.ts | Pass | Demo QA and unit tests | docs/qa/2026-06-23-production-scale-demo-qa.md | BUG-001 | Fixed | Pass | 2026-06-24 | apiMockReady false-positive noted in React Doctor config.
DEMO-002 | Dev Demo Mode | Mocked write workflows | Developer/QA | As a QA tester, I want demo workflows that show success to mutate visible state. | Demo handlers cover positions, trades, snapshots, investors, NAV, analytics, performance, prices, FX, exports, asset search, and statement parsing. | Unsupported endpoint masking real workflow, stale analytics, reset on refresh. | packages/frontend/src/dev/demoMode.tsx; packages/frontend/src/dev/__tests__/demoMode.test.ts | Pass | Demo workflow tests | docs/qa/2026-06-23-production-scale-demo-qa.md BUG-001 | BUG-001 | Fixed | Pass | 2026-06-24 | This was the first major QA gap found and fixed.
API-001 | Backend API | /api/v1/positions | Signed-in user | As a user, I want position CRUD, summary, allocation, performers, and history APIs to power portfolio views. | Routes create/update/delete only the current user's rows; summaries exclude custody; allocation/performance math handles category and storage grouping; history operations are transactional. | Cross-user ID, custody, reduce to zero, undefined LRU key in cache interaction. | packages/backend/src/routes/positions.ts; packages/backend/src/services/portfolioService.ts; packages/backend/src/lib/domain.ts | Pass | Backend route and domain tests | packages/backend/src/__tests__/routes/positions.test.ts; domain.test.ts |  | N/A | Pass | 2026-06-24
API-002 | Backend API | /api/v1/trades | Trader | As a trader, I want trade APIs to create, update, close, delete, bulk import, paginate, and calculate analytics. | Routes validate positive quantities/prices, compute LONG/SHORT PnL correctly, support pagination, and scope all writes to the current user. | Short trades, open trades, malformed bulk imports, cross-user ID. | packages/backend/src/routes/trades.ts; packages/backend/src/lib/tradePnL.ts; packages/backend/src/lib/pagination.ts | Pass | Backend route and unit tests | packages/backend/src/__tests__/routes/trades.test.ts; tradePnL.test.ts; pagination.test.ts |  | N/A | Pass | 2026-06-24
API-003 | Backend API | /api/v1/snapshots | Signed-in user | As a user, I want snapshot APIs for history tables and dashboard charts. | Routes support create/update/delete/bulk, source/type filtering, pagination/limit, performance history with all=true, monthly returns, and nested snapshot positions. | Duplicate timestamp, pending live row, 500 limit, empty positions. | packages/backend/src/routes/snapshots.ts; packages/backend/src/services/snapshotService.ts; packages/backend/src/lib/pagination.ts | Pass | Backend route tests and local QA | packages/backend/src/__tests__/routes/snapshots.test.ts; .codex-qa evidence | BUG-004; BUG-006 | Fixed | Pass | 2026-06-24
API-004 | Backend API | /api/v1/assets | Signed-in user | As a user, I want asset APIs for search, provider creation, unit trusts, NAV update, price refresh, and statement parsing. | Routes validate provider/category compatibility, apply admin/ownership guards, parse PDF statements, search provider assets, and update manual NAV. | Unsupported broker, non-admin global mutation, unowned NAV update, provider outage. | packages/backend/src/routes/assets.ts; packages/backend/src/services/providers/*; packages/backend/src/services/statementParsers/* | Pass | Backend route/parser/provider tests | packages/backend/src/__tests__/routes/assets.test.ts; YahooFinanceProvider.test.ts; fsmOneParser.test.ts |  | N/A | Pass | 2026-06-24
API-005 | Backend API | /api/v1/prices | Signed-in user | As a user, I want current prices, refresh, and historical benchmark data. | Prices refresh through providers with rate limiting/caching; historical benchmark data falls back to stored PriceHistory when providers fail and compacts same-day rows. | CoinGecko outage, Yahoo datacenter failure, same-day points, API rate limits. | packages/backend/src/routes/prices.ts; packages/backend/src/services/priceService.ts; packages/backend/src/lib/TTLCache.ts | Pass | Backend service tests and final QA | packages/backend/src/__tests__/priceService.test.ts; TTLCache.test.ts; docs/qa BUG-009 | BUG-009 | Fixed | Pass | 2026-06-24 | CoinGecko request delay is 2.1 seconds between queued calls.
API-006 | Backend API | /api/v1/fx | Signed-in user | As a user, I want FX rates for USD to supported native currencies. | FX routes expose rates, conversion, and refresh; scheduler and route share fxConstants so adding a currency is one edit. | Missing rate, zero rate, stale rate, unsupported currency. | packages/backend/src/routes/fx.ts; packages/backend/src/lib/fxConstants.ts; packages/backend/src/services/scheduler.ts | Pass | Domain parity check and route code review | npm run domain:check; docs/qa settings route |  | N/A | Pass | 2026-06-24 | Supported app native-rate fields include SGD/JPY/TWD/KRW/NOK.
API-007 | Backend API | /api/v1/export | Signed-in user | As a user, I want CSV and Excel exports for portfolio backup and analysis. | CSV endpoints stream positions/trades; Excel endpoint creates supported worksheets and avoids protected History sheet name. | Empty data, large rows, ExcelJS worksheet restrictions. | packages/backend/src/routes/export.ts; packages/backend/src/__tests__/routes/export.test.ts | Pass | HEAD export checks and export workbook tests | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json exports | BUG-005 | Fixed | Pass | 2026-06-24
OPS-001 | Operations | Express server | Operator | As an operator, I want production-safe defaults for CORS, payload size, rate limiting, logging, and startup warnings. | Server uses exact-origin CORS, 1mb JSON limit, global /api rate limiting, structured logger, Sentry init, and production warnings for missing config. | Origin prefix attacks, invalid LOG_LEVEL, missing ADMIN_USER_IDS, large import payload. | packages/backend/src/index.ts; packages/backend/src/lib/constants.ts; logger.ts; startupChecks.ts | Pass | Unit tests and code review | packages/backend/src/__tests__/logger.test.ts; startupChecks.test.ts; constants.test.ts |  | N/A | Pass | 2026-06-24
OPS-002 | Operations | Schedulers | Operator | As an operator, I want background jobs to refresh prices, FX, snapshots, and cleanup history in production. | Schedulers run only in production, initialize price/equity/FX/snapshot/cleanup jobs, catch up missing snapshots after DB connection, and broadcast relevant socket events. | Dev duplicate cron, DB not connected, broadcast fanout, provider failure. | packages/backend/src/index.ts; packages/backend/src/services/scheduler.ts; packages/backend/src/__tests__/scheduler.test.ts | Pass | Scheduler tests and code review | packages/backend/src/__tests__/scheduler.test.ts |  | N/A | Pass | 2026-06-24 | Dev server intentionally skips schedulers.
OPS-003 | Operations | Local scale QA dataset | Developer/QA | As a QA tester, I want deterministic sanitized local scale data for repeatable user behavior testing. | Seed script upserts synthetic assets, 63 positions, 240 trades, 390 snapshots, and 5 investors for LOCAL_AUTH_USER_ID without touching production data. | Existing local rows, Docker DB name mismatch, re-run idempotence. | packages/backend/src/scripts/seed-scale.ts; docs/qa/local-production-scale-runbook.md | Pass | Local seed and clean QA evidence | .codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json api.counts |  | N/A | Pass | 2026-06-24 | Final counts matched expected sanitized dataset.

## Defects
Defect ID | Title | Area | Evidence | Root Cause | Fix | Regression Test | Retest Result | Status
BUG-001 | Demo mock endpoints did not cover visible workflows | Dev Demo Mode | Visible import/CRUD workflows could show success while demo state stayed stale. | Demo mock implemented portfolio deeply but left trades, snapshots, investors, NAV, analytics, and performance shallow or generic. | Expanded demo mutable stores and handlers for trades, snapshots, investors, NAV, analytics, performance history, and resettable test state. | packages/frontend/src/dev/__tests__/demoMode.test.ts | Pass | Fixed
BUG-002 | Duplicate React keys in Dashboard performers under scale data | Dashboard | Browser console reported duplicate key cash-sgd. | Performers UI used assetId as a unique row key even when several positions shared an asset. | Key rows by assetId plus rank index. | packages/frontend/src/components/dashboard/__tests__/PerformersCard.test.tsx | Pass | Fixed
BUG-003 | Local backend bypass did not let frontend exercise authenticated routes | Auth and Runtime | Frontend still rendered Clerk sign-in while backend bypass was enabled. | Bypass existed only in backend middleware; React routes still gated on Clerk SignedIn. | Added dev-only frontend bypass and local authenticated app branch. | packages/frontend/src/lib/__tests__/localAuthBypass.test.ts | Pass | Fixed
BUG-004 | History hid the scale snapshot dataset | History | History showed All (0) while API had 390 snapshots with explicit limit. | Page called useSnapshots() with no explicit limit while backend applies default pagination. | History requests HISTORY_SNAPSHOT_LIMIT = 500 and surfaces load errors. | packages/frontend/src/hooks/__tests__/useSnapshots.test.ts | Pass | Fixed
BUG-005 | Excel export failed because History is a protected worksheet name | Exports | HEAD /api/v1/export/excel returned 500; ExcelJS rejected worksheet name History. | Workbook used user-facing route name without accounting for ExcelJS restrictions. | Renamed worksheet to Snapshots. | packages/backend/src/__tests__/routes/export.test.ts | Pass | Fixed
BUG-006 | Negative snapshot input was converted into a positive snapshot | History | Entering -1 created a manual snapshot with value 1. | FormattedNumberInput stripped leading minus and kept digits for non-negative fields. | Leading-negative input clears the field; SnapshotForm disables submit unless USD value is > 0. | packages/frontend/src/components/ui/__tests__/formatted-number-input.test.ts | Pass | Fixed
BUG-007 | Local auth bypass still depended on Clerk at runtime | Auth and Runtime | Pages crashed with useAuth outside ClerkProvider or rendered zero rows when Clerk script was blocked. | AppShell UserButton, useAuthSetup, and websocket hook still depended on Clerk. | Local bypass skips ClerkProvider, installs no-token getter, renders LB avatar, and leaves websocket disconnected. | packages/frontend/src/hooks/__tests__/useAuthSetup.test.ts; useWebSocket.test.ts | Pass | Fixed
BUG-008 | Finance forms had incomplete invalid-submit guards | Forms | TradeForm and PositionForm could be clickable or visually-only disabled for invalid finance input. | Validation split across browser required, parseFloat, and CSS while backend Zod was stricter. | Added formValidation helpers and wired Trade, Position, Add/Reduce, and Snapshot guards. | packages/frontend/src/lib/__tests__/formValidation.test.ts | Pass | Fixed
BUG-009 | Benchmark history still depended on external providers during local scale QA | Dashboard | Benchmark history API returned 500 when providers failed despite stored PriceHistory rows. | priceService delegated directly to live providers with no DB fallback. | Fallback to stored PriceHistory for matching providerAssetId/provider and compact same-day points. | packages/backend/src/__tests__/priceService.test.ts | Pass | Fixed

## Evidence
Evidence ID | Type | Path or Command | What It Covers | Status | Date
EV-001 | Fresh local QA evidence | C:/Users/User/dev/ClaudeProjs/projects/foliobuddy/.codex-qa/current-user-story-run/fresh-smoke-2026-06-24T08-11-45Z/evidence.json | Current managed server smoke: API counts, six desktop routes, mobile drawer, export HEAD checks, invalid guards, trade detail, and write-request safety. | Pass | 2026-06-24
EV-002 | Local QA evidence | C:/Users/User/dev/ClaudeProjs/projects/foliobuddy/.codex-qa/clean-inventory-2026-06-24T12-46-01/evidence.json | Final clean route matrix, export checks, interaction checks, console/network/API failure counts, and screenshots. | Pass | 2026-06-24
EV-003 | QA source inventory | docs/qa/user-facing-inventory.md | Source-backed route/control/dialog/state/API inventory and latest rerun status. | Pass | 2026-06-24
EV-004 | Real local QA report | docs/qa/2026-06-23-real-local-scale-qa.md | Local stack, sanitized seed, route matrix, interactions, bug log, clean goal pass. | Pass | 2026-06-23
EV-005 | Demo QA report | docs/qa/2026-06-23-production-scale-demo-qa.md | Dev demo route scale QA and demo-mode defects. | Pass | 2026-06-23
EV-006 | Runbook | docs/qa/local-production-scale-runbook.md | Repeatable local backend/frontend/seed/test workflow. | Ready | 2026-06-24
EV-007 | Automated tests | npm test | Backend and frontend unit/integration coverage for defects and core route behavior. | Pass in prior clean gate | 2026-06-24
EV-008 | Build | npm run build | Backend/frontend TypeScript and production build. | Pass in prior clean gate | 2026-06-24
EV-009 | Domain parity | npm run domain:check | Shared/backend domain constant parity. | Pass in prior clean gate | 2026-06-24

## Legend
Field | Allowed Values | Meaning
Test Status | Pass | Behavior has route, interaction, unit, integration, or code-review evidence.
Test Status | Needs Test | Behavior is inventoried but still needs a targeted verification pass.
Test Status | Fail | Behavior currently has an unfixed defect.
Test Status | Blocked | Behavior cannot be verified without external credentials, services, or user approval.
Fix Status | N/A | No defect is attached to this row.
Fix Status | Fixed | Known defect was fixed and regression-tested.
Fix Status | Open | Known defect still needs implementation work.
Retest Status | Pass | Behavior passed after fix or on latest clean run.
Retest Status | Pending | Behavior still needs a post-fix rerun.